## DASHBOARD
?? PROJECT & SITE PROGRESS COMMAND CENTER
OVERALL SITE PROGRESS: | 56.67%

## PARTS_MASTER
Part_ID | Part_Number | Description | Manufacturer | Unit_Cost | Initial_Stock
HW-001 | PN-7788 | Core Router | Cisco | 1200 | 10
SW-002 | LIC-9900 | Firewall License | Fortinet | 500 | 50
HW-003 | PN-5544 | Access Point | Aruba | 350 | 20
SW-004 | LIC-1122 | Monitoring Tool | SolarWinds | 800 | 100
HW-005 | PN-2233 | Switch 24-Port | Ubiquiti | 450 | 15

## BOM_PROJECT
Project_Site | Part_ID | Serial_Number | Qty_Needed
Manila_DC | HW-001 | SN-RT001 | 1
Manila_DC | SW-002 | N/A | 1
Cebu_Branch | HW-003 | SN-AP005 | 5
Davao_Office | SW-004 | N/A | 1
Manila_DC | HW-005 | SN-SW003 | 2

## SITE_PROGRESS
Site_Name | Equipment_ID | Description | Status | Completion_% | Delivery_Date | Installation_Date
Manila_DC | HW-001 | Core Router | Commissioned | 100% | 2026-05-01 | 2026-05-10
Cebu_Branch | HW-003 | Access Point | Installation | 60% | 2026-05-05
Davao_Office | SW-004 | Monitoring Tool | Pending | 10%